## Sheet1
Royal University of Phnom Penh | [5 empty] | Faculty of Engineering
Spider Robot with Esp-cam
|  | To be completed by: |  | Deadline: | Highlight Activities
|  | Khiev Noren and Chorn Chhorm |  | 19/6/2023 | This Year [2023]
Action | Responsible | Start Date | End Date | Budget | Progress | Note
Week #1: Researching
Inverse kenematic | Both | 18/02/2023 | 2023-04-03
Robot Simulation | Both | 18/02/2023 | 2023-04-03
3D design | Both | 25/02/2023 | 2023-04-03
Discussing | Both | 22/02/2023 | 2023-04-03
Week #3: Hardware/software
3d design( printing ) | Chorn Chormm | 2023-05-03 | 2023-12-03
Solfware | Khiev Noren | 2023-05-03 | 19/03/2023
Finalize hardware | Both | 2023-08-03 | 19/03/2023
Discussing | Both | 2023-08-03 | 19/03/2023
Week #5: Solfware
Real-time testing | Chorn Chormm | 20/03/2023 | 27/03/2023
Algorithm | Both | 23/03/2023 | 28/03/2023
Solfware | Khiev Noren | 20/03/2023 | 2023-03-04
Discussing | Both | 23/03/2023 | 2023-03-05
Week #7: Solfware Testing
Robot Config | Both | 2023-04-04 | 2023-11-04
Robot Config | Both | 2023-04-04 | 2023-11-04
Solfware | Both | 2023-04-04 | 2023-11-04
Discussing | Both | 2023-04-04 | 2023-11-04
Week #8: Research
RF24 communication | Chorn Chormm | 11/04//2023 | 25/04/2023
ESP-CAM live feat | Khiev Noren | 11/04//2023 | 25/04/2023
Circuit Design | Both | 18/04/2023 | 25/04/2023
Discussing | Both | 18/04/2023 | 25/04/2023
Week #11: Hardware and Software
PCB design | Chorn Chormm | 26/04/2023 | 2023-03-05
PCB (Mounting) | Chorn Chormm | 26/04/2023 | 2023-10-05
Solfware | Khiev Noren | 26/04/2023 | 2023-10-05
Discussing | Both | 2023-03-05 | 2023-10-05
Week #13: Connecting
Robot and controller | Chorn Chormm | 2023-11-05 | 18/05/2023
ESP-CAM Mount | Khiev Noren | 2023-11-05 | 18/05/2023
ESP-CAM CHECK | Khiev Noren | 2023-11-05 | 18/05/2023
Discussing | Both | 2023-11-05 | 18/05/2023
Week #14: Restesting
Softwares updates | Khiev Noren | 19/05/2023 | 2023-02-06
Hardwares | Chorn Chormm | 19/05/2023 | 2023-02-06
Discussing | Both | 19/05/2023 | 2023-02-06
Week #16: Final Retesting
Hardware checkup | Chorn Chormm | 2023-05-06 | 19/06/2023
Softwares check up | Khiev Noren | 2023-05-06 | 19/06/2023